## Team
Initials | First | Last | Email | GitHub Username
XX | Xiaomeng | Xu | sherman77.xu@gmail.com | Sherman77
ZZ2 | Ziyu | Zhang | zcvszzy@gmail.com | SamNormcoreWayne
ZZ1 | Zheng | Zhou | nicole.zhouzhenggca@gmail.com | nikou0986
PL | Puzhuo | Li | puzhouli@gmail.com | JamesLi0217
GitHub Repository:
SamNormcoreWayne/SSW555_TeamPrj
URL:
https://github.com/SamNormcoreWayne/SSW555_TeamPrj

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Birth before current date | Zheng Zhou | complete
| US02 | Birth before marriage | Zheng Zhou | complete
| US03 | Birth before death | Xiaomeng Xu | complete
| US04 | Marriage before divorce | Xiaomeng Xu | complete
| US05 | Marriage before death | Puzhuo Li | complete
| US06 | Divorce before death | Puzhuo Li | complete
| US07 | Less then 150 years old | Ziyu Zhang | complete
| US10 | Marriage after 14 | Ziyu Zhang | complete
2 | US08 | Birth before marriage of parents | Ziyu Zhang | complete
| US09 | Birth before death of parents | Zheng Zhou | complete
| US11 | No bigamy | Puzhuo Li | complete
| US12 | Parents not too old | Puzhuo Li | complete
| US13 | Siblings spacing | Xiaomeng Xu | complete
| US14 | Multiple births <= 5 | Zheng Zhou | complete
| US15 | Fewer than 15 siblings | Xiaomeng Xu | complete
| US16 | Male last names | Ziyu Zhang | complete
3 | US17 | No marriages to children | Puzhuo Li | complete
| US18 | Siblings should not marry | Puzhuo LI | complete
| US19 | First cousins should not marry | Ziyu Zhang | complete
| US20 | Aunts and uncles | Ziyu Zhang | complete
| US21 | Correct gender for role | Zheng Zhou | complete
| US22 | Unique IDs | Zheng Zhou | complete
| US23 | Unique name and birth date | Xiaomeng Xu | complete
| US24 | Unique families by spouses | Xiaomeng Xu | complete
4 | US25 | Unique first names in families | Ziyu Zhang | complete
| US26 | Corresponding entries | Ziyu Zhang | complete
| US27 | Include individual ages | Puzhuo Li | complete
| US28 | Order siblings by age | Puzhuo Li | complete
| US29 | List deceased | Zheng Zhou | complete
| US30 | List living married | Zheng Zhou | complete
| US31 | List living single | Xiaomeng Xu | complete
| US32 | List multiple births | Xiaomeng Xu | complete

## Burndown README (hidden)
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2016-06-06 | 24 |  | 0
Sprint 1 | 2016-06-19 | 18 | #REF! | 250 | 120 | 125
Sprint 2 | 2016-07-03 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2016-07-17 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2016-07-31 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Stories
Story ID | Story Name | Story Description
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date
US02 | Birth before marriage | Birth should occur before marriage of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US05 | Marriage before death | Marriage should occur before death of either spouse
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US16 | Male last names | All male members of a family should have the same last name
US17 | No marriages to children | Parents should not marry any of their children
US18 | Siblings should not marry | Siblings should not marry one another
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file
US30 | List living married | List all living married people in a GEDCOM file
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate)

## Burndown
Sprint | Date | Remaining Stories | Story Velocity | LOC | Hours | Code Velocity
Start | 2019-01-20 | 32 |  | 0 | 0
Sprint 1 | 2019-02-08 | 24 | 8 | 177 | 51.5 | 177
Sprint 2 | 2019-02-22 | 16 | 8 | 385 | 50 | 4.16
Sprint 3 | 2019-03-25 | 8 | 8 | 542 | 55 | 2.8545
Sprint 4 | [5 empty] | #REF!

## Sprint1
Story ID | Story Name | Owner/Tester | Developer | Status | Est Size | Est Time(h) | Act Size | Act Time (h) | Completed | Source File | Source Function | Source Lines | Test File | Test Function | Test lines
US03 | Birth before death | XX | PL | complete | 150 | 3.5 | 42 | 6 |  | GED.py | us03_birth_b4_death | 212 - 254 | TestGED_us03_us04.py | Test_us03_birth_b4_death | 9 - 38
T03.01 | Store birth date
T03.02 | Store death date
T03.03 | Compare birth and death dates
US05 | Marriage before death | PL | XX | complete | 150 | 3.5 | 25 | 8 |  | GED.py | us05_marriage_b4_death | 278 - 303 | TestGED_us05.py | Test_us05_marriage_b4_death | 11 - 45
T05.01 | Find individual death date
T05.02 | Find marriage date
T05.03 | Compare marriage date to death date
US02 | Birth before marriage | ZZ1 | XX | complete | 150 | 3.5 | 23 | 8 |  | GED.py | us02_birth_b4_marriage | 186 - 209 | TestGED_us02.py | Test_us02_birth_b4_marriage | 8 - 42
T02.01 | Store individual birth date
T02.02 | Store marriage date
T02.03 | Compare marriage date to birth date
US04 | Marriage before divorce | XX | PL | complete | 150 | 3.5 | 18 | 6 |  | GED.py | us04_marriage_b4_divoce | 257 - 275 | TestGED_us03_us04.py | Test_us04_marriage_b4_divoce | 43 - 59
T04.01 | Store marriage date
T04.02 | Store divorce date
T04.03 | Compare marriage date with divorce date
US06 | Divorce before death | PL | ZZ2 | complete | 150 | 3.5 | 39 | 5.5 |  | GED.py | compare_divrdate_ddate | 306 - 345 | TestGED_us06.py | test_store_divorce_date | 18 - 24
T06.01 | Store divorce date | [12 empty] | test_store_death_date | 26 - 32
T06.02 | Store death date if applicable | [12 empty] | test_compare_divrdate_ddate | 34 - 39
T06.03 | Compare marriage date with divorce date
complete
US07 | Less then 150 years old | ZZ2 | ZZ1 | complete | 150 | 2 | 10 | 5 |  | GED.py | us07_age_less_150 | 348 - 358 | TestGED_us07.py | test_age_less_150 | 47 - 61
T07.01 | Store birth date
T07.02 | Calculate age
T07.03 | Compare age with 150
complete
US01 | Birth before current date | ZZ1 | ZZ2 | complete | 150 | 4 | 3 | 6 |  | GED.py | us_01_birth_b4_now | 180 - 183 | TestGED_us01.py | test_birth_b4_now | 19 - 27
T01.01 | Store individual birthday
T01.02 | Compare to current date
T01.03 | Generate output
complete
US10 | Marriage after 14 | ZZ2 | ZZ1 | complete | 150 | 4 | 17 | 7 |  | GED.py | us10_marriage_after_14 | 361 - 378 | TestGED_us10.py | Test_us_10_01 | 11 - 28
T10.01 | Store individual birthday | [12 empty] | Test_us_10_02 | 30 - 47
T10.02 | Store individual marriage date
T10.03 | Compare marriage date to 14th birthday
T10.04 | Generate output
Rewiew Result | *See attached report
Keep Doing | 1. Participate in daily standup meetings.
2. Daily communication
3. Regular updates on Github and Spreadsheet
4. Regular code reviews
5. Learn from other groups
6. Standraize code style
Avoid | 1. Merge into master branch until the last minute
2. Overestimate/underestimate LOC
3. Unevenly distributed work
4. Debug in the late stage
5. Update spreadsheet until the last minute

## Sprint2
Story ID | Story Name | Owner | Developer | Status | Est Size | Est Time | Act Size | Act Time | Completed | Source File | Source Function | Source Lines | Test File | Test Function | Test lines
US08 | Birth before marriage of parents | ZZ2 | PL | complete | 250 | 8 | 24 | 8 |  | GED.py | us08_birth_b4_parents_marriage() | 415 ~ 439 | test/TestGED_t08.py | test_us08_birth_b4_parents_marriage() | 20 ~ 22
T08.01 | find birth date
T08.02 | find married date
T08.03 | find divorce date
T08.04 | compare birth and married date
T08.05 | compare birth and divorce date
US09 | Birth before death of parents | ZZ1 | PL/XX | complete | 250 | 8 | 67 | 10 |  | GED.py | us09_birth_b4_parents_death() | 441 ~ 508 | test/TestGED_t09.py | test_us09_birth_b4_parents_death() | 20 ~ 22
T09.01 | find birth date
T09.02 | find mother death date
T09.03 | find father death date
T09.04 | compare birth and mother death date
T09.05 | compare birth and father death date
US11 | No bigamy | PL | ZZ1 / ZZ2 | complete | 200 | 10 | 21 | 6 |  | GED.py | US11_No_Bigamy() | 610 ~ 631 | test/TestGED_t11.py | test_US11_No_Bigamy() | 19 ~ 33
T11.01 | Find number of marriages of individual
T11.02 | If marriage >1, find the divorce date of the former marriage
T11.03 | Find the marriage date of the latter marriage
T11.04 | Compare divorce date with marriage date
US12 | Parents not too old | PL | ZZ2 | complete | 150 | 8 | 37 | 6 |  | GED.py | us12_parents_not_2_old() | 536 ~ 573 | test/TestGED_t12.py | test_us12_parents_not_2_old() | 28 ~ 48
T12.01 | find mother age
T12.02 | find father age
T12.03 | find individual age
T12.04 | compare mother age and individual(diff<60)
T12.05 | compare father age and individual(diff<80)
US13 | Sibling spacing | XX | ZZ2 / ZZ1 | complete | 250 | 12 | 27 | 12 |  | GED.py | us13_sibling_spacing() | 667 ~ 694 | test/TestGED_t13.py | test_US13_sibling_spacing() | 20 ~ 33
T13.01 | Birthday exists
T13.02 | Have Siblings
T13.03 | More than 8 months or less than 2 days
US14 | Multiple births <= 5 | ZZ1 | XX/PL | complete | 150 | 8 | 33 | 6 |  | GED.py | us14_multiple_birth_less_5() | 575 ~ 608 | test/TestGED_t14.py | test_family_a() test_family_b() | 11 ~ 20
T14.01 | find children id in families
T14.02 | compare children birth date
T14.03 | check if more than 5 children were born on the same day
US15 | Fewer than 15 siblings | XX | ZZ2/ZZ1 | complete | 150 | 8 | 9 | 10 |  | GED.py | US15_Fewer_15_Child() | 633 ~ 642 | test/TestGED_t15.py | test_us15() | 20 ~ 36
T15.01 | find number of children in families
T15.02 | compare number of children with 15
US16 | Male last names | ZZ2 | XX | complete | 100 | 8 | 11 | 8 |  | GED.py | us16_male_last_names() | 644 ~ 655 | test/TestGED_t16.py | test_family_a() test_family_b() | 11 ~ 25
T16.01 | Look for huabend's name
T16.02 | Look for child's name
T16.03 | Check if they have the same last name
Review Results
Keep doing: | 1. Daily communication
2. Pair programing
3. Constantly process reivew
4. Refactoring
Avoid: | 1. Inconsistent code style
2. Creating too many branches

## Sprint3
Story ID | Story Name | Owner | Developer | Status | Est Size | Est Time | Act Size | Act Time | Completed | Source File | Source Function | Source Lines | Test File | Test Function | Test lines
US17 | No marriages to children | XX | PL | complete | 30 | 5 | 18 | 7 |  | GED.py | us17_No_marriages_to_children | 738-756 | TestGED_us17.py | test_US17_No_marriages_to_children() | 19-28
T17.01 | get hus id
T17.02 | if hus id equal to chid id, compare their wife id
T17.03 | get the true or false result
US18 | Siblings should not marry | ZZ1 | PL | complete | 30 | 7 | 13 | 8 |  | GED.py | us18_Siblings_should_not_marry | 758-771 | TestGED_us18.py | test_US18_Siblings_should_not_marry() | 19-28
T18.01 | get hus and wife id
t18.02 | use the id to obtain their couples
t18.03 | compare and check if the couples are in same famlily
US19 | First cousins should not marry | ZZ1 | ZZ2 | complete | 25 | 8 | 23 | 8 |  | GED.py | us_19_cousins_not_marry | 773-796 | TestGED_us19.py | test_us19_cousins_not_marry() | 2019-11-15
T19.01 | get all children information including gender
T19.02 | find children's cousins
T19.03 | check if they are in same family
US20 | Aunts and uncles | PL | ZZ2 | complete | 20 | 8 | 42 | 7 |  | GED.py | us20_aunts_uncle | 798-840 | TestGED_us20.py | test_us20_aunts_uncle() | 2019-11-16
T20.01 | get children id,gender,mother id,father id
T20.02 | find aunt information
T20.03 | check the aunt if have hus who is chid's uncle
US21 | Correct gender for role | XX | ZZ1 | complete | 20 | 10 | 12 | 5 |  | GED.py | us21_correct_gender | 696-708 | TestGED_us21.py | test_US21_correct_gender() | 19-26
T21.01 | get all hus id and wife id in fam
T21.02 | check the gender
T21.03 | return results
US22 | Unique ID | ZZ2 | ZZ1 | complete | 20 | 10 | 10 | 5 |  | GED.py | us22_unique_indi_IDs | 710-720 | TestGED_us22.py | test_US22_unique_fam_IDs() | 20-27
T22.01 | get all people id and store in a list | [12 empty] | test_US22_unique_indi_IDs() | 29-31
T22.02 | check if the list equal to set(list)
T22.03
US23 | Unique name and birth date | PL | XX | complete | 25 | 4 | 23 | 5 |  | GED.py | us23_unique_name_and_birthday | 842-865 | TestGED_us23.py | test_us23_a() | 2019-11-27
T23.01 | get all people's name and birthdate | [12 empty] | test_us23_b() | 31-36
T23.02 | store name and birthdate in list
T23.03 | check if the list equal to set(list)
US24 | Unique families by spouses | ZZ2 | XX | complete | 25 | 4 | 25 | 5 |  | GED.py | us24_unique_family_by_spouse | 867-889 | TestGED_us24.py | Test_us24_a() | 2019-11-16
T24.01 | get all the information of hus and wife | [12 empty] | test_us24_b() | 18-25
T24.02 | check if same hus name and wife in same famliy exists
Review Results
Keep doing: | 1. keep coding style consistent
2. finsh the work on time
3. update github as soon as possible
4. frequent integration
Avoid: | 1. Place files under false branches
2. Having less daily meetings

## Sprint4
Story ID | Story Name | Owner | Developer | Status | Est Size | Est Time | Act Size | Act Time | Completed
US25 | Unique first names in families | XX | ZZ1
T25.01
T25.02
T25.03
US26 | Corresponding entries | ZZ1 | ZZ1
T26.01
T26.02
T26.03
US27 | Include individual ages | ZZ2 | PL
T27.01
T27.02
T27.03
US28 | Order siblings by age | PL | PL
T28.01
T28.02
T28.03
US29 | List deceased | XX | ZZ1
T29.01
T29.02
T29.03
US30 | List living married | ZZ2 | ZZ1
T30.01
T30.02
T30.03
US31 | List living single | ZZ2 | PL
T31.01
T31.02
T31.03
US32 | List all multiple births in a GEDCOM file | PL | ZZ2
T32.01
T32.02
T32.03